## Sheet1
tasks | start house | minutes spent day 1 | minutes spent day 2 | minutes spent day 3 | minutes spent day 4 | minutes spent day 5 | minutes spent day 6 | minutes spent day 7 | minutes spent day 8 | minutes spent day 9 | minutes spent day 10 | total Hours
task 1 :User login | 20 | 240 | 80 | 60 | 40 | 20 | 20 | 20 | 10 | 0 | 0 | 8.1667
task 2 :Add sales record | 18 | 240 | 180 | 150 | 120 | 90 | 80 | 60 | 30 | 10 | 0 | 16
task 3: Word suggestion | 14 | 120 | 40 | 40 | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 4.1667
tasks 4 :Confirm record | 13 | 120 | 40 | 40 | 40 | 20 | 10 | 0 | 0 | 0 | 0 | 4.5
tasks :5 stock level | 2 | 200 | 70 | 50 | 50 | 50 | 10 | 0 | 0 | 0 | 0 | 7.1667
total estimated hours | 40 | 920 | 410 | 340 | 270 | 200 | 130 | 80 | 40 | 10 | 0
total actual hours | 40.6667 | 920 | 420 | 300 | 300 | 200 | 150 | 90 | 40 | 20 | 0
total estimated hours | 40 | 920 | 410 | 340 | 270 | 200 | 130 | 80 | 40 | 10 | 0
total actual hours | 40.6667 | 920 | 420 | 300 | 300 | 200 | 150 | 90 | 40 | 20 | 0

## Sheet2
tasks | start house | hours spent day 1 | hours spent day 2 | hours spent day 3 | hours spent day 4 | hours spent day 5 | hours spent day 6 | hours spent day 7 | hours spent day 8 | hours spent day 9 | hours spent day 10 | total Hours
task 1 User login | 20 | 240 | 70 | 60 | 40 | 20 | 20 | 20 | 10 | 0 | 0 | 8
task 2 Add sales record | 18 | 240 | 180 | 140 | 120 | 90 | 80 | 60 | 40 | 10 | 0 | 16
task 3 Word suggestion | 14 | 120 | 40 | 40 | 20 | 10 | 10 | 0 | 0 | 0 | 0 | 4
tasks 4 Confirm record | 13 | 120 | 40 | 30 | 30 | 10 | 10 | 0 | 0 | 0 | 0 | 4
tasks 5 stock level | 2 | 200 | 70 | 50 | 50 | 50 | 20 | 20 | 20 | 0 | 0 | 8
total estimated hours | 40 | 920 | 400 | 320 | 260 | 180 | 140 | 100 | 70 | 10 | 0
total actual hours | 40.6667 | 920 | 420 | 300 | 300 | 200 | 150 | 90 | 40 | 20 | 0